General Assembly, Sofia, March 5th, 2013

National Palace of Culture, Hall 7

Draft

ACTION PLAN

for 2013

NB: Activities throughout the year will be geared the 10th anniversary of the adoption of the Convention (2003)

| December 2012 |  | Drafting of the documents for the General Assembly in 2013 |
| --- | --- | --- |
|  |  | Drafting of the amendments to the Statutes |
|  |  | Sending, at their request, an invitation to Armenia to join the Centre |
| January 2013 |  | Translation and sending out of the document for the General Assembly for approval by the UNESCO Secretariat: |
|  |  | - Activity report for 2012 - Financial report - Draft amendments to the Statutes - Draft amendments to the Staffing Table - Draft action plan for 2013. |
| February 2013 |  | Drafting and sending out of letters of invitation to the States participating in the work of the Centre |
|  |  | Drafting and sending out of letters of invitation to the heads of ICH Category 2 Centres for participation in the meeting for exchange of experience and good practices |
| March 5th, 2013 |  | General Assembly of the South-East Europe States participating in the work of the Centre |
| March 2013 |  | Sending out of a circular letter to the SEE States, Moldova and Armenia, to: - launch a common film project for SEE on ‘Ritual Games and Masks on SEE’ (terms and parameters for the individual States’ films) - Drafting the Rules for Presentation of the traditional cuisine of SEE States during the Bansko Folklore Festival (Bulgaria) - Sending out of letters of invitation for participation in the Presentation of the traditional cuisine of SEE States during the Bansko Folklore Festival (end of May 2013) |
| April 2013 |  | Training seminar for national staff of Greece in the key concepts of the 2003 Convention and identification of ICH elements (in a city chosen by Greece) |
| May 2013 |  | Seventh regional meeting of ICH experts from SEE (jointly with BRESCE) |
| June 2013 |  | Training seminar for national staff of Southwest Bulgaria, in the key concepts of the 2003 Convention and identification of ICH elements (in the town of …………) |
| June 24th, 2013 |  | Gala concert to mark the 10th anniversary of the 2003 Convention |
| Beginning of July 2013 |  | Meeting of the heads of ICH Centres of UNESCO Category 2 for exchange of information, experience and good practices |
| September 2013 |  | Participation of the SEE States willing to do so in the Ethno Music Section of the Apollonia Festival (in the town of Sozopol, Bulgaria) |
| End of September 2013 |  | Training seminar for national staff of FYROM in the key concepts of the 2003 Convention and identification of ICH elements (in a city chosen by FYROM) |
| October 4th-8th, 2013 |  | Participation on the Festival of Ethnological Documentary Films (Belgrade, Serbia) |
|  |  | Conference on ‘Copyrighting in the area of the intangible cultural heritage’ (subject to UNESCO approval) |
| November 2013 |  | Premiere of the common film project of SEE States on ‘Ritual Games and Masks on SEE’ |
|  |  | Participation in the UNESCO General Conference |
| December 2013 |  | Participation in the Eight Session of the ICH Committee (Azerbaijan) |

Note: Training seminars, the subject matters of those and the meeting of heads of UNESCO Category 2 centres, as well as the two States: Greece and FYROM, were determined by UNESCO. The format for such training seminars is 25-30 persons at most, duration: 4 days + 2 for travel; duration of the centres’ meeting: 2 + 2 days.

Also envisioned are visits by Mrs. Yolanda Valle-Neff, the BRESCE Director, to Bulgaria, and by the Executive Director of the Regional Centre to FYROM, Turkey and Greece.